{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Allgemein","Prüfplan","Tabelle3"],"not_rendered":{"images":1,"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"Allgemein","index":0,"n_rows":42,"n_cols":14,"rows_kept":42,"merged":[[3,1,3,13],[4,1,4,13],[5,1,5,13]]}
[]
[]
[]
[null,"Standort"]
[null,"Projekt"]
[null,"ID-Nummer"]
[]
[]
[null,"PQM Prüf- und Kontrollplan ",{"$nulls":11},"2013-02-11"]
[]
[]
[null,"Ausgangslage"]
[null,"Der Prüf- und Kontrollplan ist Teil des PQM. Er dient auf der Stufe der Ausführung als Instrument zur Überwachung und Kontrolle der Bauarbeiten und zur Qualitätssicherung."]
[null,"Er ist vor der Realisierung, zum Zeitpunkt der Ausschreibung, in Zusammenarbeit mit den Fachplanern durch die Projektleitung Bau zu erstellen."]
[null,"Die Checklisten Qualitätssicherung Bau ist durch die Planer zu erstellen und den Ausschreibungen beizulegen. "]
[null,"Der Prüf- und Kontrollplan ist durch die Projektleitung Bau sowie die Checklisten Qualitätssicherung durch die entsprechenden Planer zu führen und entsprechend dem Bauvortschritt zu aktualisieren. "]
[]
[null,"Ausführungs- und Baukontrolle"]
[null,"Die Ausführungskontrolle findet in Form von Rundgängen und stichprobenartigen Detailkontrollen auf der Baustelle statt."]
[null,"Die Kontrollen (gemäss den Prüfpunkten der Checkliste Qualitätssicherung Bau und des Prüf- und Kontrollplans) sind zeitnah nach der Erstellung durchzuführen. "]
[null,"Jeder Rundgang wird mit einem kurzen Journal dokumentiert und allfällig mit Digitalfotos ergänzt. "]
[null,"Zusätzliche Nachweise gemäss Checkliste Qualitätssicherung Bau werden beigelegt."]
[null,"Die Ablage erfolgt in Ordner welche bei der Bauleitung deponiert sind."]
[null,"Erhebliche Mängel, Reklamationen, Einwände und Hinweise sind der Projektleitung Bauherr zu melden."]
[]
[null,"Prüfpunkte"]
[null,"Als Grundlage für die detaillierte Kontrolle dient die Checkliste Qualitätssicherung Bau."]
[null,"Für jede Arbeitsgattung werden die wichtigsten Kontrollpunkte und wenn nötig die spezifische Nachweisdokumente definiert."]
[null,"Der Prüf- und Kontrollplan ist laufend den aktuellen Gegebenheiten und dem Baufortschritt anzupassen. "]
[]
[null,"Im wesentlichen werden folgende Punkte kontrolliert:"]
[null,"- Qualitätskontrollen der Ausführunge nach Arbeitsgattung (gemäss Checkliste)"]
[null,"- Stichproben über Produkte und verwendete Materialien gemäss Wervertrag und Vorgaben Ökologie"]
[null,"- Arbeitssicherheit, Einhaltung der SUVA-Vorschriften"]
[null,"- Schutzvorkehrungen für bereits montierte Bauteile"]
[null,"- Kontrolle des Baufortschrittes"]
[]
[null,"Index"]
[null,"Verantwortlich: U = Untenehmer / BL = Bauleitung / FBL = Fachbauleitung / PL Bau = Projektleitung Bau / PL Bauherr = Projektleitung Bauherr"]
[null,"Nachweisdokument: P = Protokoll / CH = Checkliste / BJ = Baujournal"]
[null,"Intensität: per = periodisch / lau = laufend / bei = bei Bedarf"]
[null,"Status: E = Erfüllt / TE = teilweise erfüllt / NE = nicht erfüllt / P = Pendent / NK = nachträgliche Kontrolle BL"]

{"sheet":"Prüfplan","index":1,"n_rows":254,"n_cols":14,"rows_kept":254,"merged":[[3,1,3,13],[4,1,4,13],[5,1,5,13],[11,4,12,4],[11,5,12,5],[11,6,12,6],[11,7,12,7],[11,8,12,8],[11,10,12,10],[11,11,12,11],[11,12,12,12]]}
[]
[]
[]
[null,"Standort"]
[null,"Projekt"]
[null,"ID-Nummer"]
[]
[]
[null,"PQM Prüf- und Kontrollplan ",{"$nulls":11},"2013-02-11"]
[]
[]
[null,"BKP","Arbeitsgattung",null,"Verantwortlich für die Durchführung","Kontrollpartner","Nachweisdokument","Rapporte / Nachweis zu Handen","Intensität der Kontrolle",null,"Datum geplant","Datum Prüfung","Status"]
[null,"Nr.","QM Prüfpunkte / Kontrollen","Lage",{"$nulls":5},"Termin",{"$nulls":3},"Bemerkung, Protokoll Nr., Checkliste Nr."]
[]
[null,112,"Abbrüche"]
[null,{"v":1,"d":"01"},"Abbruchkonzept / Sicherheit","Gesamt","U","PL Bau","P","BL",null,"gem. Bauprogramm"]
[null,{"v":2,"d":"02"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,113,"Demontagen"]
[null,{"v":1,"d":"01"},"Entsorgungskonzept","Gesamt","U","PL Bau","P","BL",null,"gem. Bauprogramm"]
[null,{"v":2,"d":"02"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,121,"Sicherung vorhandener Anlagen"]
[null,{"v":1,"d":"01"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,122,"Provisorien"]
[null,{"v":1,"d":"01"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,201,"Baugrubenaushub"]
[null,{"v":1,"d":"01"},"Masskontrolle Absteckung","Gesamt","U","BL","P","BL",null,"gem. Bauprogramm"]
[null,{"v":2,"d":"02"},"Kontrolle Böschungen, Humusdeponie ",null,"BL","U","BJ","BL","lau"]
[null,{"v":2,"d":"02"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,{"v":211,"d":"211.0"},"Baumeisterarbeiten"]
[null,{"v":1,"d":"01"},"Kontrolle Abschrankungen","Gesamt","BL","U","BJ",null,"per","laufend"]
[null,{"v":2,"d":"02"},"Masskontrolle am Bau","Gesamt","U","-","Plan","BL","lau"]
[null,{"v":3,"d":"03"},"Kontrolle Material, Ausführung","Gesamt","BL","U","BJ",null,"per","laufend"]
[null,{"v":4,"d":"04"},"Abnahme Schalung Decken / Wände","Stockwerksweise","Bauing","Polier","Notiz","Bauing","per","vor betonieren"]
[null,{"v":5,"d":"05"},"Abnahme Armierung Decken / Wände  ","Stockwerksweise","Bauing","Polier","Notiz","Bauing","per","vor betonieren"]
[null,{"v":6,"d":"06"},"Betonprüfung (Material / Druck)","Stockwerksweise","Bauing","Polier","Notiz","Bauing","per","nach betonieren"]
[null,{"v":7,"d":"07"},"Endabnahme nach SIA","Gesamt","BL","U/Bauing.","P","PL Bauherr",null,"nach Fertigstellung"]
[null,211.1,"Gerüstungen"]
[null,{"v":1,"d":"01"},"Kontrolle Bauaufzüge nach Installation","Bauaufzüge","U","-","P","BL","lau"]
[null,{"v":2,"d":"02"},"Prüfen Sicherheit nach den SUVA-Vorschriften","Gesamt","U","-","P","BL","alle 2 Wochen"]
[null,212,"Montagebau in Beton"]
[null,{"v":1,"d":"01"},"Masskontrolle am Bau","Gesamt","U","-","Plan","BL","lau"]
[null,{"v":2,"d":"02"},"Kontrollpläne Ausführung Elemente","Gesamt","U","PL Bau","Plan","PL","lau","gem. Bauprogramm"]
[null,{"v":3,"d":"03"},"Kontrolle Ausführung, Oberfläche und Befestigung",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":4,"d":"04"},"Kontrolle Schutz während Bauphase",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,213,"Montagebau in Stahl"]
[null,{"v":1,"d":"01"},"Masskontrolle am Bau","Gesamt","U","-","Plan","BL","lau"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Oberfläche und Befestigung",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":3,"d":"03"},"Kontrolle Schutz während Bauphase",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":4,"d":"04"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,214,"Montagebau in Holz"]
[null,{"v":1,"d":"01"},"Masskontrolle am Bau","Gesamt","U","-","Plan","BL","lau"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Oberfläche und Befestigung",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":3,"d":"03"},"Kontrolle Schutz während Bauphase",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":4,"d":"04"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,215,"Montagebau als Leichtkonstruktion (Fassadenbau)"]
[null,{"v":1,"d":"01"},"Masskontrolle am Bau","Gesamt","U","-","Plan","BL","lau"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Oberfläche und Befestigung",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":3,"d":"03"},"Kontrolle Schutz während Bauphase",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":4,"d":"04"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,216,"Natur- und Kunststeinarbeiten"]
[null,{"v":1,"d":"01"},"Masskontrolle am Bau","Gesamt","U","-","Plan","BL","lau"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Oberfläche und Befestigung",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":3,"d":"03"},"Kontrolle Schutz während Bauphase",null,"BL","U","BJ","BL","per","laufend"]
[null,{"v":4,"d":"04"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,221.1,"Fenster aus Holz/Metall"]
[null,{"v":1,"d":"01"},"Massaufnahme am Bau","Gesamt","U","-","Plan","BL","lau"]
[null,{"v":2,"d":"02"},"Kontrollpläne Ausführung Fenster","Gesamt","U","PL Bau","Plan","PL","lau","gem. Bauprogramm"]
[null,{"v":3,"d":"03"},"Abnahme der Montage, Glas-Sichtkontrolle, Beschläge, Abdichtungen, Anschlüsse, Funktion, Beschädigungen  ","Stockwerksweise","BL","U","P","BL",null,"nach erfolgter Montage ev. Zwischenabnahmen"]
[null,{"v":4,"d":"04"},"Dichtigkeitskontrolle aussen und innen","Stockwerksweise","BL","U","P","BL"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,221.4,"Fenster aus Aluminium"]
[null,{"v":1,"d":"01"},"Massaufnahme am Bau","Gesamt","U","-","Plan","BL","lau"]
[null,{"v":2,"d":"02"},"Kontrollpläne Ausführung Fenster","Gesamt","U","PL Bau","Plan","PL","lau","gem. Bauprogramm"]
[null,{"v":3,"d":"03"},"Abnahme der Montage, Glas-Sichtkontrolle, Beschläge, Abdichtungen, Anschlüsse, Funktion, Beschädigungen  ","Stockwerksweise","BL","U","P","BL",null,"nach erfolgter Montage ev. Zwischenabnahmen"]
[null,{"v":4,"d":"04"},"Dichtigkeitskontrolle aussen und innen","Stockwerksweise","BL","U","P","BL","per"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,223,"Blitzschutz"]
[null,{"v":1,"d":"01"},"Planung, Bewilligung GVL","Gesamt","PL","U","P","PL"]
[null,{"v":2,"d":"02"},"Abnahme POT-Ausgleich","Gesamt","BL","U","P","BL",null,"nach Fertigstellung Rohbau"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA (inkl. Messung)","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,{"v":224,"d":"224.0"},"Deckungen (Steildächer)"]
[null,{"v":1,"d":"01"},"Kontrolle Ausführung, Material",null,"BL","U","P","BL","lau"]
[null,{"v":1,"d":"01"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,224.1,"Plastische und elastische Dichtungsbeläge (Flachdächer)"]
[null,{"v":1,"d":"01"},"Prüfung Untergrund","Gesamt","U","BL","P","BL"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material",null,"BL","U","P","BL","lau"]
[null,{"v":3,"d":"03"},"Dichtigkeitskontrolle Dampfsperre/Notdach","Gesamt","U","BL","P","BL"]
[null,{"v":4,"d":"04"},"Dichtigkeitskontrolle Dachhaut, Anschlüsse","Gesamt","U","BL","P","BL"]
[null,{"v":5,"d":"05"},"Abnahme Dachhaut nach Montage","Gesamt","U","BL","P","BL"]
[null,{"v":6,"d":"06"},"Abnahme Substrat nach Einbringen","Gesamt","U","BL","P","BL"]
[null,{"v":7,"d":"07"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,225.1,"Fugendichtungen"]
[null,{"v":1,"d":"01"},"Prüfung Untergrund","Gesamt","U","BL","P","BL"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material",null,"BL","U","P","BL","lau"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,225.4,"Brandschutzbekleidungen"]
[null,{"v":1,"d":"01"},"Kontrolle Steigschächte, Vorabnahme GVL","Stockwerksweise","BL","U","P","PL Bauherr",null,"vor schliessen des Schächte "]
[null,{"v":2,"d":"02"},"Kontrolle Decken/Wanddurchbrüche, Vorabnahme GVL","Stockwerksweise","BL","U","P","PL Bauherr",null,"vor schliessen der Decken"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA mit GVL","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,226,"Fassadenputze"]
[null,{"v":1,"d":"01"},"Prüfung Untergrund","Gesamt","U","BL","P","BL"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Aufbau, Fristen",null,"BL","U","P","BL","lau"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,227,"Äussere Oberflächenbehandlungen"]
[null,{"v":1,"d":"01"},"Prüfung Untergrund","Gesamt","U","BL","P","BL"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Aufbau, Fristen",null,"BL","U","P","BL","lau"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,228.2,"Lamellenstoren"]
[null,{"v":1,"d":"01"},"Massaufnahme am Bau","Gesamt","U","-","Plan"]
[null,{"v":2,"d":"02"},"Abnahme der Montage ","Gesamt","BL","U","P"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,230,"Elektroinstallationen"]
[null,{"v":1,"d":"01"},"Arbeitssicherheit: Kontrolle ob Sicherheitsbestimmungen bezüglich Arbeitskleidung und Werkzeuge eingehalten werden und ob auf Notfallsituationen reagiert werden kann (Verbandskasten, Notfallnummern, etc.)","Gesamt","FBL","-","BJ","-","lau","wöchentlich",{"$nulls":3},"Bei Gespräch mit Elektrikern vor Ort wird auf dies geachtet"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material",null,"FBL","U","P","BL","lau"]
[null,{"v":3,"d":"03"},"Installationsabnahme","Stockwerksweise","FBL","U","P","BL",null,"nach erfolgter Montage und vor schliessen der Wände/Schächte"]
[null,232,"Starkstrominstallationen"]
[null,{"v":1,"d":"01"},"Rohbauabnahme","Stockweise","FBL","U","P","BL","bei","nach Beendigung von nächster Rohbauetappe",{"$nulls":3},"Rohbauabnahme mit Kontrolle der Anschlusspunkte und Leitungsführung"]
[null,{"v":2,"d":"02"},"Sichtprüfungen","Gesamt","FBL","U","BJ","BL","bei","Sichtprüfung der Installation auf Vorschriftseinhaltung und Sauberkeit",{"$nulls":3},"Steigzonen horizontal/vertikal, Verkabelung Verteilungen"]
[null,{"v":3,"d":"03"},"Funktionskontrolle","Gesamt","FBL","U","P","BL","bei","Funktionskontrolle der Installationen",{"$nulls":3},"Beleuchtung/Kraft durch Testen"]
[null,{"v":4,"d":"04"},"Erstellen des Sicherheitsnachweises (SINA)","Gesamt","electro-suisse","U/FBL","SINA","BL","bei","gemäss Vorschrift zu erstellen"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,233,"Leuchten und Lampen"]
[null,{"v":1,"d":"01"},"Provisorische Beleuchtung","Gesamt","FBL","U","BJ","BL","lau","wöchentlich",{"$nulls":3},"Kontrolle, ob Lichtstärke in Treppenhäusern und Korridoren die Sicherheit noch gewährleisten"]
[null,{"v":2,"d":"02"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,236,"Schwachstrominstallationen"]
[null,{"v":1,"d":"01"},"Funktionskontrolle","Gesamt","FBL","U","P","BL","bei","Funktionskontrolle der Installationen",{"$nulls":3},"Schwachstromverkabelung durch Messprotokolle"]
[null,{"v":2,"d":"02"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,237,"Gebäudeautomation"]
[null,{"v":1,"d":"01"},"Funktionskontrolle, Punkttest","Gesamt","FBL","U","P","BL","bei","Funktionskontrolle der Installationen",{"$nulls":3},"Messprotokolle"]
[null,{"v":2,"d":"02"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,240,"Heizungs-, Lüftungs-, Klimaanlagen"]
[null,{"v":1,"d":"01"},"Kontrolle Ausführung, Material",null,"FBL","U","P","BL","lau"]
[null,{"v":2,"d":"02"},"Installationsabnahme","Stockwerksweise","FBL","U","P","BL",null,"nach erfolgter Montage und vor schliessen der Wände/Schächte"]
[null,242,"Wärmeerzeugung"]
[null,{"v":1,"d":"01"},"Abnahme der Montage ","Stockwerksweise","FBL","U","BJ","BL",null,"periodisch"," "]
[null,{"v":2,"d":"02"},"Dichtigkeitskontrolle","Fassadenweise","U","FBL","P","BL",null,"nach Baufortschritt"]
[null,{"v":3,"d":"03"},"Funktionskontrolle ","Gesamt","FBL","U","P","BL"]
[null,{"v":4,"d":"04"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,244,"Lüftungsanlagen"]
[null,{"v":1,"d":"01"},"Abnahme der Montage ","Stockwerksweise","FBL","U","BJ","BL",null,"periodisch"]
[null,{"v":2,"d":"02"},"Funktionskontrolle ","Gesamt","FBL","U","P","BL"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,245,"Klimanlagen"]
[null,{"v":1,"d":"01"},"Abnahme der Montage ","Stockwerksweise","FBL","U","BJ","BL",null,"periodisch"]
[null,{"v":2,"d":"02"},"Dichtigkeitskontrolle","Fassadenweise","U","FBL","P","BL",null,"nach Baufortschritt"]
[null,{"v":3,"d":"03"},"Funktionskontrolle ","Gesamt","FBL","U","P","BL"]
[null,{"v":4,"d":"04"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,247,"Spezialanlagen "]
[null,{"v":1,"d":"01"},"Abnahme der Montage ","Stockwerksweise","FBL","U","BJ","BL",null,"periodisch"]
[null,{"v":2,"d":"02"},"Funktionskontrolle ","Gesamt","FBL","U","P","BL"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,250,"Sanitäranlagen"]
[null,{"v":1,"d":"01"},"Kontrolle Ausführung, Material",null,"FBL","U","P","BL","lau"]
[null,{"v":2,"d":"02"},"Installationsabnahme","Stockwerksweise","FBL","U","P","BL",null,"nach erfolgter Montage und vor schliessen der Wände/Schächte"]
[null,251,"Allgemeine Sanitärapparate"]
[null,{"v":1,"d":"01"},"Abnahme der Apparate","Stockwerksweise","FBL","U","P","BL",null,"laufen"]
[null,{"v":2,"d":"02"},"Funktionskontrolle ","Gesamt","FBL","U","P","BL"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U/FBL","P","PL Bauherr",null,"nach Fertigstellung"]
[null,258,"Kücheneinrichtungen"]
[null,{"v":1,"d":"01"},"Massaufnahme am Bau",null,"U","PL Bau","P","BL",null,"gem. Bauprogramm"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material",null,"FBL","U","P","BL"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr"]
[null,261,"Aufzüge"]
[null,{"v":1,"d":"01"},"Liftschachtkontrolle (Rohbau, Maler, Beleuchtung, Entlüftung, Gerüst)",null,"BL","U","P","BL",null,"vor Montagebeginn"]
[null,{"v":2,"d":"02"},"Funktionskontrolle (Steuerung, Notrufsystem)","Gesamt","BL","U","P","BL"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,{"v":271,"d":"271.0"},"Verputzarbeiten (innere)"]
[null,{"v":1,"d":"01"},"Prüfung Untergrund","Gesamt","U","BL","P","BL"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Putzstärken, Massgenauigkeit",null,"BL","U","BJ"]
[null,{"v":3,"d":"03"},"Abnahme Oberflächen für anschliessende Malerarbeiten","Stockwerksweise","BL","U","BJ",null,null,"laufend"]
[null,{"v":4,"d":"04"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,271.1,"Spezielle Gipserarbeiten"]
[null,{"v":1,"d":"01"},"Massaufkontrolle am Bau",null,"U","-","Plan","BL","lau"]
[null,{"v":2,"d":"02"},"Kontrolle der Ständerverstärkungen, Vorabnahme Aussteifungskonstruktionen / Schallschutz",null,"BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,{"v":3,"d":"03"},"Freigabe Leichtbauwände zum Schliessen (Aufnahme und Dokumentierung der Ausholzung)","Stockwerksweise","BL","U","BJ",null,null,"nach Abnahme Installationen"]
[null,{"v":4,"d":"04"},"Abnahme Oberflächen für anschliessende Tapezier- und Malerarbeiten","Stockwerksweise","BL","U","BJ",null,null,"laufend"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,{"v":272,"d":"272.0"},"Innentüren aus Metall"]
[null,{"v":1,"d":"01"},"Abnahme Vorarbeiten am Bau","Gesamt","BL","U","P","BL",null,"vor Montagebeginn"]
[null,{"v":2,"d":"02"},"Massaufnahme am Bau","Gesamt","U","-","Plan"]
[null,{"v":3,"d":"03"},"Kontrollpläne - Türliste Ausführung Türen","Gesamt","U","PL Bau","Plan","BL","lau","gem. Bauprogramm"]
[null,{"v":4,"d":"04"},"Kontrolle Ausführung, Material, Brandkennziffer, Zargen- und Rahmenbefestigung, Beschläge, Funktion",null,"BL","U","BJ"]
[null,{"v":5,"d":"05"},"Abnahme der Montage ","Gesamt","BL","U","P"]
[null,{"v":6,"d":"06"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,272.2,"Allgemeine Metallbauarbeiten (Schlosserarbeiten)"]
[null,{"v":1,"d":"01"},"Massaufnahme am Bau","Gesamt","U","-","Plan"]
[null,{"v":2,"d":"02"},"Kontrollpläne - Ausführung Metallbauarbeiten","Gesamt","U","PL Bau","Plan","BL","lau","gem. Bauprogramm"]
[null,{"v":3,"d":"03"},"Kontrolle Ausführung, Material, Massgenauigkeit",null,"BL","U","BJ"]
[null,{"v":4,"d":"04"},"Abnahme der Montage ","Gesamt","BL","U","P"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,{"v":273,"d":"273.0"},"Innentüren aus Holz"]
[null,{"v":1,"d":"01"},"Abnahme Vorarbeiten am Bau","Gesamt","BL","U","P","BL",null,"vor Montagebeginn"]
[null,{"v":2,"d":"02"},"Massaufnahme am Bau","Gesamt","U","-","Plan"]
[null,{"v":3,"d":"03"},"Kontrollpläne - Türliste Ausführung Türen","Gesamt","U","PL Bau","Plan","BL","lau","gem. Bauprogramm"]
[null,{"v":4,"d":"04"},"Kontrolle Ausführung, Material, Brandkennziffer, Zargen- und Rahmenbefestigung, Beschläge, Funktion",null,"BL","U","BJ"]
[null,{"v":5,"d":"05"},"Abnahme der Montage ","Gesamt","BL","U","P"]
[null,{"v":6,"d":"06"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,273.1,"Wandschränke, Gestelle und dgl."]
[null,{"v":1,"d":"01"},"Massaufnahme am Bau","Gesamt","U","-","Plan"]
[null,{"v":2,"d":"02"},"Kontrollpläne Ausführung Schränke, Gestelle","Gesamt","U","PL Bau","Plan","BL","lau","gem. Bauprogramm"]
[null,{"v":3,"d":"03"},"Kontrolle Ausführung, Material, Brandkennziffer, Anschlüsse, Beschläge, Funktion",null,"BL","U","BJ"]
[null,{"v":4,"d":"04"},"Abnahme der Montage ","Gesamt","BL","U","P"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,273.3,"Allgemeine Schreinerarbeiten"]
[null,{"v":1,"d":"01"},"Massaufnahme am Bau","Gesamt","U","-","Plan"]
[null,{"v":2,"d":"02"},"Kontrollpläne Ausführung Schreinerarbeiten","Gesamt","U","PL Bau","Plan","BL","lau","gem. Bauprogramm"]
[null,{"v":3,"d":"03"},"Kontrolle Ausführung, Material, Brandkennziffer",null,"BL","U","BJ"]
[null,{"v":4,"d":"04"},"Abnahme der Montage ","Gesamt","BL","U","P"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,275,"Schliessanlage"]
[null,{"v":1,"d":"01"},"Abnahme Vorarbeiten am Bau","Gesamt","BL","U","P","BL",null,"vor Montagebeginn"]
[null,{"v":2,"d":"02"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,{"v":277,"d":"277.0"},"Elementwände"]
[null,{"v":1,"d":"01"},"Massaufnahme am Bau","Gesamt","U","-","Plan"]
[null,{"v":2,"d":"02"},"Kontrollpläne Ausführung Elementwände","Gesamt","U","PL Bau","Plan","PL","lau","gem. Bauprogramm"]
[null,{"v":3,"d":"03"},"Kontrolle Ausführung, Material, Brandkennziffer, Anschlüsse, Beschläge, Funktion, Schallschutz",null,"BL","U","BJ"]
[null,{"v":4,"d":"04"},"Abnahme der Montage ","Gesamt","BL","U","P"]
[null,{"v":5,"d":"05"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,{"v":281,"d":"281.0"},"Unterlagsböden"]
[null,{"v":1,"d":"01"},"Höhenaufnahmen am Bau","Gesamt","U","BL","P","BL"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Raumklima, Fristen Austrocknung ",null,"BL","U","BJ"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,281.1,"Fugenlose Bodenbeläge"]
[null,{"v":1,"d":"01"},"Abnahme Unterlagsboden und Prüfung Restfeuchtigkeit","Stockwerksweise","U","BL","P","BL",null,"laufen"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Raumklima, Fristen Aushärtung",null,"BL","U","BJ"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,281.2,"Bodenbeläge aus Kunststoff, Textilien und dgl."]
[null,{"v":1,"d":"01"},"Abnahme Unterlagsboden und Prüfung Restfeuchtigkeit","Stockwerksweise","U","BL","P","BL",null,"laufen"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material ",null,"BL","U","BJ"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,281.6,"Bodenbeläge Plattenarbeiten"]
[null,{"v":1,"d":"01"},"Abnahme Unterlagsboden und Prüfung Restfeuchtigkeit","Stockwerksweise","U","BL","P","BL",null,"laufen"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material ",null,"BL","U","BJ"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,281.7,"Bodenbeläge aus Holz"]
[null,{"v":1,"d":"01"},"Abnahme Unterlagsboden und Prüfung Restfeuchtigkeit","Stockwerksweise","U","BL","P","BL",null,"laufend"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Fristen Versiegelung ",null,"BL","U","BJ"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,282,"Wandbeläge, Wandbekleidungen"]
[null,{"v":1,"d":"01"},"Abnahme Wandoberfläche und Prüfung Restfeuchtigkeit","Stockwerksweise","U","BL","P","BL"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material ",null,"BL","U","BJ"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,283,"Deckenbekleidungen "]
[null,{"v":1,"d":"01"},"Kontrolle Ausführung, Material, Abhänghöhen, Anschlüsse, Ausschnitte, Akustik ",null,"BL","U","BJ"]
[null,{"v":2,"d":"02"},"Abnahme nach Montage","Stockwerksweise","U","BL","P","BL"]
[null,{"v":3,"d":"03"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,285,"Innere Oberflächenbehandlungen"]
[null,{"v":1,"d":"01"},"Prüfung Untergrund","Gesamt","U","BL","P","BL"]
[null,{"v":2,"d":"02"},"Kontrolle Ausführung, Material, Farbenummer, Aufbau,Gleichmässigkeit",null,"BL","U","BJ"]
[null,{"v":3,"d":"03"},"Abnahme Deckenoberflächen ","Stockwerksweise","U","BL","P","BL",null,"laufend"]
[null,{"v":4,"d":"04"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]
[null,287,"Baureinigung"]
[null,{"v":1,"d":"01"},"Endabnahme nach SIA","Gesamt","BL","U","P","PL Bauherr",null,"nach Fertigstellung"]

{"sheet":"Tabelle3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"hidden":true}